## TI_PD_I2C_Address
PD Address - Port 1 & 2
LOW Cost Solution Modules 203, 800 | [5 empty] | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C0 Address (PD-PPC) | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | TPS66993BAREPR (20 V SPR PROD Part) PTPS66993BAREPT (PRE-PROD part) | 0x20 | 0x50 |  | 0 | 0 | 0 | 0 | 1M | A93548-209 | R6L2 | Unstuff | 1M | A93548-209 | R6L1 | Stuff
PPC Address
TCP1 | Redriver + PPC Controller | TPS66990G1BAREPR (20V SPR PROD part) PTPS66990G1BAREPT (PRE_PROD part) PTPS66990G1EBAREPT (28V EPR Pre-PROD part) | 0x24 | 0x51 | 0x1E For PPC 0x0D(RDR Address) |  |  |  |  | 1K | H30143-022 | R6L2 | Stuff | 100K | H30143-005 | R6L1 | Unstuff
TI TBT Module -103 | [5 empty] | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN
DDR5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | TPS66993BAREPR (20 V SPR PROD Part) PTPS66993BAREPT (PRE-PROD part) | 0x20 | 0x50 | 0x58 | 0 | 0 | 0 | 0 | 1M | A93548-209 | R6L2 | Unstuff | 1M | A93548-209 | R6L1 | Stuff
TI TBT Module -103 | [5 empty] | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | TPS66993BAREPR (20 V SPR PROD Part) PTPS66993BAREPT (PRE-PROD part) | 0x20 | 0x50 | 0x58 | 0 | 0 | 0 | 0 | 1M | A93548-209 | R6L2 | Unstuff | 1M | A93548-209 | R6L1 | Stuff
[6 empty] | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP1 | Single Port PD Controller | TPS66993BAREPR (20 V SPR PROD Part) PTPS66993BAREPT (PRE-PROD part) | 0x21 | 0x51 | 0x58 | 0 | 1 | 0 | 0 | 1M | A93548-209 | R1N5 | Stuff | 287k | A36092-464 | R1N7 | Stuff

## ANX_PD_I2C_Address
PD ADDRESS - Port 1
LOW Cost Solution Modules 204, 801 | [6 empty] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C0 Address (PD-PPC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | ANX7407FN-AA-R | 0x58 | 0x50 |  |  | 1K | H30143-022 | R6L2 | Unstuff | 1M | C48657-005 | R6L1 | Stuff
PPC ADDRESS - Port 2
TCP1 | Redriver + PPC Controller | ANX7495QN-AA-R (REDRIVER + PPC ) | 0x80 (8 bit addressing corres. To 0x40 7-bit address) | 0x51 | 0x8E (RDR address - 8 bit addressing ) |  | 4.7K | A93549-020 | R6L2 | Unstuff | 100K | H30143-005 | R6L1 | Stuff
RDR ADDRESS
[7 empty] | 4.7K | A93549-020 | R6L2 | Stuff | 100K | A93549-020 | R6L1 | Unstuff

## Realtek_PD_I2C_Address (chrome)
Realtek TBT Module -106 | [5 empty] | RUP |  |  |  | RDOWN
DDR5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | RTS5452P-GR | 0x21 | 0x50 | 0x58 | 150k | A36092-305 | R1M27 | Stuff | 34k | A36092-405 | R1M28 | Stuff
Realtek TBT Module -106 | [5 empty] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | RTS5452P-GR | 0x22 | 0x50 | 0x58 | 150K |  | R1P9 | Stuff | 56.2K |  | R1P8 | Stuff
[6 empty] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP1 | Single Port PD Controller | RTS5452P-GR | 0x20 | 0x51 | 0x58 | 1M | A93548-209 | R6L2 | Unstuff | 1M | A93548-209 | R6L1 | Stuff
|  |  |  | TI | RTK | RTK
|  |  | DDR5 | 20 | 20 | 21
|  |  | LP5 | 21 | 20 | 22
|  |  | LP5 | 22 | 21 | 20

## GBR_PD_I2C_Address
GBR TBT Module -702 | [5 empty] | RUP |  |  |  | RDOWN
DDR5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C Address (PD/TCPC address) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | GBR - A2 Silicon | 0x56 | 0x50 | 0x50 | 100K | A93548-128 | R6L2 | Stuff | 60.4K | A93548-199 | R6L1 | Stuff
TCP1 | Single Port PD Controller | GBR - A2 Silicon | 0x57 | 0x51 | 0x50 | 100K | A93548-128 | R6L2 | Stuff | 76.8K | A93548-576 | R6L1 | Stuff
GBR TBT Module -702 | [5 empty] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single Port PD Controller | GBR - A2 Silicon | 0x56 | 0x50 | 0x50 | 100K | A93548-209 | R6L2 | Stuff | 60.4K | A93548-199 | R6L1 | Stuff
[6 empty] | RUP |  |  |  | RDOWN
LP5 SKU |  |  | I2C1 Address (PD-EC) | I2C2 Address (PD-PMC) | I2C3 Address (PD-RTMR) | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP1 | Single Port PD Controller | GBR - A2 Silicon | 0x57 | 0x51 | 0x50 | 100K | A93548-128 | R1M27 | Stuff | 76.8K | A93548-576 | R1M28 | Stuff

## WCL PD I2C Address
As per SPR datasheet
|  |  | I2C1 Address (TI) | Adddress / Current | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN |  |  |  | Configuration | Modules expected to Plug IN
WCL DDR5: |  |  |  | Sink_disable | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single port PD | PTPS66993AAREPT | 0x21 | #1 | 0 | 1 | 0 | 0 | 1M | A93548-209 | R1N6 | Stuff | 287k | A36092-464 | R1N8132 | Stuff | Modular TCSS1 | TA,ADD-IN CARD,PTL-UH,TCSS 103 - USBC RETIMER
| Single GBR |  | TBD | #1
WCL LP5 |  |  | I2C1 Address (TI) | Adddress / Current | ADCIN[3] | ADCIN[2] | ADCIN[1] | ADCIN[0] | RUP |  |  |  | RDOWN |  |  |  | Configuration
|  |  |  | SinkRequires_disable | x | x | 0 | 0 | Value | IPN | Refdes | Stuff / Unstuff | Value | IPN | Refdes | Stuff / Unstuff
TCP0 | Single port PD | PTPS66993AAREPT | 0x20 | #1 | 0 | 0 | 0 | 0 | 1M | A93548-209 | R1P10 | Unstuff | 1M | A93548-209 | R1P9 | Stuff | Modular TCSS1
TCP1 | Single port PD | PTPS66993AAREPT | 0x21 | #2 | 0 | 1 | 0 | 0 | 1M | A93548-209 | R1N6 | Stuff | 287k | A36092-464 | R1N8 | Stuff | Modular TCSS2

## EEPROM_MODULE (RVP)
DDR5 SKU
TCP0 - EEPROM ADDRESS
EEPROM address - 0x54 - 100 (A2, A1, A0)
I2C_ADDR0
PU | R1P26 | 1k | A93549-016 | UNSTUFF
PD | R2P15 | 100k | A93549-027 | STUFF
I2C_ADDR1
PU | R1P24 | 1k | A93549-016 | UNSTUFF
PD | R2P14 | 100k | A93549-027 | STUFF
LP5 SKU
TCP0 - EEPROM ADDRESS
EEPROM address - 0x54 - 100 (A2, A1, A0)
I2C_ADDR0
PU | R1P26 | 1k | A93549-016 | UNSTUFF
PD | R2P15 | 100k | A93549-027 | STUFF
I2C_ADDR1
PU | R1P24 | 1k | A93549-016 | UNSTUFF
PD | R2P14 | 100k | A93549-027 | STUFF
TCP1 - EEPROM ADDRESS
EEPROM address - 0x55 - 101 (A2, A1, A0)
I2C_ADDR0
PU | R1P26 | 1k | A93549-016 | STUFF
PD | R2P15 | 100k | A93549-027 | UNSTUFF
I2C_ADDR1
PU | R1P24 | 1k | A93549-016 | UNSTUFF
PD | R2P14 | 100k | A93549-027 | STUFF
Module Name | EEPROM value bin (16bit) | EEPROM value hex
TCSS Card103, 900- TBT-40G Retimer (TI) Volume | 100100101001011 | 494B
TCSS Card104 - TBT-40G Retimer (CCG) | 100101001001011 | 4A4B
TCSS Card105 - TBT-40G Retimer (RTK) Chrome | 100101101001011 | 4B4B
TCSS Card301 - HDMI 12Gbps Redriver Volume | 10000000001111 | 200F
TCSS Card302 - HDMI 12Gbps Retimer | 10000000001111 | 200F
TCSS Card500,501 - eDP module | 10111 | 17
TCSS Card600 - Type A redriverless | 111 | 7
TCSS Card700 - Gothic Bridge (pending CCB) | 100110001001011 | 4C4B
TCSS Card701 - Gothic Bridge with Hayden Bridge (pending CCB) | 100110010001011 | 4C8B
TCSS card 702 single GBR Module |  | 4C4B
TCSS Card 203 TI Retimerless Module
TCSS card 204 ANX Retimerless Module
TCSS card 800 TI Redriver + PPC Module
TCSS card 801 ANX Redriver + PPC Module
TCSS card 106 Realtek TBT + CCD Module |  | 4B4B

## TCSS_PCH_GPIO(RVP)
Type C Port -0 |  | Type C Port -0
PCH GPIO | Signal Netname (Device end) | PCH GPIO | Signal Netname (Device end)
HSIO SIGNALS
TYPEC_0_TXRX1_DP | TCP0_TXRX1_DP | TYPEC_1_TXRX1_DP | TCP1_TXRX1_DP
TYPEC_0_TXRX1_DN | TCP0_TXRX1_DN | TYPEC_1_TXRX1_DN | TCP1_TXRX1_DN
TYPEC_0_TXRX0_DP | TCP0_TXRX0_DP | TYPEC_1_TXRX0_DP | TCP1_TXRX0_DP
TYPEC_0_TXRX0_DN | TCP0_TXRX0_DN | TYPEC_1_TXRX0_DN | TCP1_TXRX0_DN
TYPEC_0_TX1_DP | TCP0_TX1_DP | TYPEC_1_TX1_DP | TCP1_TX1_DP
TYPEC_0_TX1_DN | TCP0_TX1_DN | TYPEC_1_TX1_DN | TCP1_TX1_DN
TYPEC_0_TX0_DP | TCP0_TX0_DP | TYPEC_1_TX0_DP | TCP1_TX0_DP
TYPEC_0_TX0_DN | TCP0_TX0_DN | TYPEC_1_TX0_DN | TCP1_TX0_DN
TYPEC_0_AUXPAD_DP | TCP0_AUX_R_DP | TYPEC_1_AUXPAD_DP | TCP1_AUX_DP
TYPEC_0_AUXPAD_DN | TCP0_AUX_R_DN | TYPEC_1_AUXPAD_DN | TCP1_AUX_DN
GPP_C16_TBT_LSX0_A_DDP1_CTRLCLK | MOD_TCSS1_LS_TX_DDC_SCL | GPP_C18_TBT_LSX1_A_DDP2_CTRLCLK | TBT_LSX1_TXD
GPP_C17_TBT_LSX0_B_DDP1_CTRLDATA | MOD_TCSS1_LS_RX_DDC_SDA | GPP_C19_TBT_LSX1_B_DDP2_CTRLDATA | TBT_LSX1_RXD
I3C DEBUG SIGNALS
GPP_H24_BPKI3C_SCL | MOD_TCSS_DEBUG_I3C_SCL_DP | GPP_H24_BPKI3C_SCL | TCP1_DEBUG_I3C_SCL
GPP_H23_BPKI3C_SDA | MOD_TCSS_DEBUG_I3C_SDA_DN | GPP_H23_BPKI3C_SDA | TCP1_DEBUG_I3C_SDA
USB2 SIGNALS
USB2_1_DP | USB2_P1_TCSS_MODULE1_DP | USB2_2_DP | TCP_PB_USB2_CONN_DP
USB2_1_DN | USB2_P1_TCSS_MODULE1_DN | USB2_2_DN | TCP_PB_USB2_CONN_DN
SML SIGNALS
GPP_C3_SML0CLK | TCP_LAN_SML0_SCL_R | GPP_C3_SML0CLK | TCP_LAN_SML0_SCL_R
GPP_C4_SML0DATA | TCP_LAN_SML0_SDA_R | GPP_C4_SML0DATA | TCP_LAN_SML0_SDA_R
PD-PMC I2C SIGNALS
GPP_B0_USBC_SMLCLK | MOD_TCSS1_PD_PMC_SML1_SCL | GPP_B0_USBC_SMLCLK | SML_PD_I2C_SCL
GPP_B1_USBC_SMLDATA | MOD_TCSS1_PD_PMC_SML1_SDA | GPP_B1_USBC_SMLDATA | SML_PD_I2C_SDA
GPP_E21_PMC_ALERT_N | MOD_TCSS1_PD_PMC_SML1_INT | GPP_E21_PMC_ALERT_N | SML_PD_I2C_INT#
CONTROL SIGNALS
GPP_B9_DDSP_HPD1_DISP_MISC1 | MOD_TCSS1_DISP_HPD1
GPP_D19_TBT_LSX0_OE | MOD_TCSS1_LSX_DIR_SEL
GPP_C8_SML1ALERT_N_PCHHOT_N | TCP_RT_S0IX_ENTRY_EXIT_N
GPP_D1_I2C3A_SDA_ISH_I2C2A_SDA | MOD_TCSS1_TYP_A_VBUS_EN
GPP_B21_I2C5A_SCL_CNV_MFUART0_CTS_N_ISH_GP_9 | TCP_RETIMER_FORCE_PWR
GPP_E9_USB2_OC0_N | MOD_TCSS_USB_TYP_A_OC0_N
GPP_V14_FORCEPR_N | MOD_TCSS1_PROCHOT_N

## Module_latest_schedule(RVP)
WCL TCSS Modules | PROTO FAB1 TO | PROTO FAB2 TO | Availability in LAB | Val. Completion | Go & No-Go for Volume build | Volume Build for RVP | ERB Build | ERB Availability | ERB PO | Applicable RVP
M.2 GBR (HBR+PD) - MB Short length | WW32 | May/May not | WW38/WW39 | 6 Weeks. (WW44) | WW44 | WW05 | WW46 | WW48 | WW48 | RVP1 & RVP2
USB3.2 Gen2 to Type A. (Redriverless) | Re-use | Not required | Re-use |  | Re-use |  |  |  |  | RVP1 & RVP2
M.2 HBR - MB Long length. | Re-use | Not required | Re-use |  | Re-use |  |  |  |  | RVP1 & RVP2
TI PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length | WW22 | Not required | WW28/WW29 | 6 Weeks. (WW38) | WW40 |  |  |  |  | RVP2
Third party ( TI ) redriver USB3.0/DP1.4 (HBR3) - Long length | WW22 | Required when is the next TO & Build ? | WW28/WW29 | 6 Weeks. (WW38) | WW40 |  |  |  |  | RVP2
Anx PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length | WW34//WW36 (2 weeks shift) | May/May not | WW40/41 | 6 Weeks.(WW46) | WW46 |  |  |  |  | RVP2
Third party (AnX) redriver USB3.0/DP1.4 (HBR3) - Long length | WW34//WW36 (2 weeks shift) | May/May not | WW40/WW41 | 6 Weeks. (WW46) | WW46 |  |  |  |  | RVP2
WCL Realtek PD TCSS Module (40G RETIMER RTK) | ~WW34 | Not required | WW42/WW43 | 6 Weeks. (WW46) | WW46 |  |  |  |  | RVP1 & RVP2
Note: ERB PO needs the Green Highlighted modules.
TCSS Modules | Controller details | SW readiness with PTL ERB validation
AIC -Type C Retimer-less 3rd party TCPM TCSS module - TI | PD- PTPS66993AAREPT | EC FW – Proprietary PTL EC firmware will be reuse to shift left validation. BIOS FW – Reuse from PTL. PD FW – TI Retimerless Module - Checkout is 91% completed with I2C0, I2C3 firmware drop. Yet to receive Common I2C0 firmware drop from TI. AR: Diana to help on this. (Int. ETA WW31) TI Redriver Module – Checkout is 87% completed . USB3 renumeration issue is observed, debug is WIP. TI meeting is scheduled to root cause the issue.
AIC - 3rd Party Redriver TCSS module - TI | PPC- PTPS66990G1REPT
Redriver - USB1044RNQR
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In case re-spin is WW45 is TO then board availability in WW51.
Note on F3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WW41 is a check point from validation side.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Post WW42 since layout review need focus on ERB. Its ok as these cards are needed for RVP - WW05 onwards.
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If we slip to WW35, WW36 TO then Build schedule timeline ?
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Velan to come up with Build week.

## Details of AIC(RVP)
WCL TCSS
| RVP1 (DDR5) |  | RVP2 (LP5)
TCP0 | Config 1: M.2 GBR (HBR+PD) - MB Short length |  | Third PD , Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length |  | TCP0 & TCP1 shared the M.2 Module paths for I2C, CC, PWR. Due to PPC , Redriver and PD Controller
Config-1
Config 2 | Config 2: USB3.2 Gen2 to Type A. (Redriverless) |  | M.2 HBR - MB short length
Config-3 | Config 3: M.2 Modular TCSS - TBT 40G Single Re-Timer. (Single Retimer HBR) |  | M.2 GBR (HBR+PD) - MB Short length
TCP1 | GBR (HBR+PD) - Solder down - Long Length |  | Third party ( TI & AnX) redriver USB3.0/DP1.4 (HBR3) - Long length
Config 1
M.2 HBR - MB Long length.
Config 2
M.2 GBR (HBR+PD)
Config-3
|  | For AIC Designing |  |  |  | Validation Vehicle | Timeline
|  | M.2 GBR (HBR+PD) - MB Short length |  | New Design in WCL ( Refer to Reference design) | Take the reference from Dual GBR in PTL. | PTL
|  | USB3.2 Gen2 to Type A. (Redriverless) |  | Direct Reuse from PTL |  | PTL
|  | M.2 HBR - MB Long length. |  | Direct Reuse from PTL |  | PTL
|  | TI PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length |  | Design leaverage from TCSS 200 design | 70% leaverage from TCSS 200 | PTL
|  | Anx PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length |  | New Design in WCL | Redefining the pinout and new AIC design which could be leaverage from ANX Redriver solution | PTL
|  | Third party ( TI ) redriver USB3.0/DP1.4 (HBR3) - Long length |  | I believe, design leaverage from TCSS 200 design | 70% leaverage from TCSS 200 | PTL
|  | Third party (AnX) redriver USB3.0/DP1.4 (HBR3) - Long length |  | New Design in WCL | Redefining the pinout and new AIC design which could be leaverage from ANX Redriver solution | PTL
AR on USHA : Align to get support from BIOS team & PD Fw team.
For On-board Design
GBR (HBR+PD) - Solder down - Long Length
Available AIC |  | Customer to use RVP1 | Customer to use RVP2
M.2 GBR (HBR+PD) - MB Short length |  | 1 | 2
USB3.2 Gen2 to Type A. (Redriverless) |  | 1 | 0
M.2 HBR - MB Long length. |  |  | 2
TI PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length |  |  | 1
Anx PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length |  |  | [
Third party ( TI ) redriver USB3.0/DP1.4 (HBR3) - Long length |  |  | 1
Third party (AnX) redriver USB3.0/DP1.4 (HBR3) - Long length |  |  | 1

## TCSS AIC BOM IPN's(RVP)
For AIC Designing
M.2 GBR (HBR+PD) - MB Short length | TA, ADD-IN-CARD, WCL,TCSS 702 - USBC GBR RETIMER. | TA- N45935-100 AA - N45934-100 PBA - N45933-100 PB - N45932-001 MP - N49983-001 |  | Reference IPN for Creating the BOM IPN
USB3.2 Gen2 to Type A. (Redriverless) | TA,ADD-IN CARD,PTL-P RVP,TCSS 600 -USBAREDRIVERLESS | Direct Reuse from PTL TA - N38705-100 AA - N38707-100 PBA - N38708-100 PB - N38709-001
M.2 HBR - MB Long length. | TA,ADD-IN CARD,PTL-UH,TCSS 103 - USBC RETIMER | Direct Reuse from PTL PB - N38766-001 PBA - N38765-100 AA - N38732-100 TA - N38727-100
TI PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length | TA, ADD-IN-CARD, WCL,TCSS 203 - USBC TI-PD RETIMERLESS. | TA - N45940-100 AA - N45939-100 PBA - N45938-100 PB -N45936-001 MP - N46930 -001
N34133-001
Anx PD Controller, Type C port - USB3/DP1.4 (HBR3) - Retimerless - MB Short length | TA, ADD-IN-CARD, WCL,TCSS 204 - USBC ANX-PD RETIMERLESS | TA - N46063-100 AA - N46062-100 PBA - N46041-100 PB - N46035-001 MP - N52978-001
Third party ( TI ) redriver USB3.0/DP1.4 (HBR3) - Long length | TA, ADD-IN-CARD, WCL,TCSS 800 - USBC TI-REDRIVER+PPC | TA - N46067-100 AA - N46066-100 PBA - N46065-100 PB - N46064-001 MP- N46915 -001
Third party (AnX) redriver USB3.0/DP1.4 (HBR3) - Long length | TA, ADD-IN-CARD, WCL,TCSS 801 - USBC ANX-REDRIVER+PPC | TA - N46084-100 AA - N46083-100 PBA - N46075-100 PB - N46069-001 MP- N52850-001
WCL Realtek PD TCSS Module (40G RETIMER RTK) | TA,ADD-IN CARD,PTL-P RVP,TCSS 106-USBC 40G RETIMER(RTK) | TA- N50779-100 AA - N50782-100 PBA - N50783-100 PB - N50838-001 MP - N52984-001 | RTK PD FW IPN -N65303-001