## RVP Wishlist
RVP1,RVP1-PPV,RVP1-PNP,RVP2,RVP3,RVP3-PnP,RVP3_MECC,RVP4,RVP4-PnP,RVP5,RVP6 | [6 empty] | Change needed in ( SKU Name) | [7 empty] | Implementation status
SL No | Wish list Description | Reason for not implemented in ERB ( if applicable) | DE owner | area of impact | SCH Impact | Layout impact | RVP 01 | RVP 02 | RVP 03 | RVP 04 | RVP 04-m | RVP 05 | RVP 06 | RVP 07 | ERB | WW18 ERB | RVP1 PRE-PO | RVP1 POST-PO | RVP 02 | RVP 03 | RVP 04 | RVP 04-m | RVP 05 | RVP 06 | RVP 07
1 | TCSS MODULE eUSB2 repeater address setting on RVP | In ERB it should not have any impact since we will be using on eUSB2 repeaters on RVP | Harshali/Naseef | TCSS |  |  | Change needed in ( SKU Name) RVP 01: All SKUs where we have mod TCSS; Change needed in ( SKU Name) RVP 03: Yes |  |  | Pending
2 | Need to give SLP S3 enable to the 12A VR for the Longtam card which needs 12S | There is no +V 12S in our RVP currently | Aparna/Vishal/Sreedevi/ Gokul/Divya |  | Yes | Yes | Change needed in ( SKU Name) RVP 01: RVP 01; Change needed in ( SKU Name) RVP 02: Not supported |  |  | Pending | Not supported | Not supported | Not supported | Not supported | Not supported | Not supported | Not supported | Not supported
3 | Remove R1f2. - TP_MCIO_SB_PORT1_PERST_LS_N | Cannot intercept in ERB due to design freeze | Aparna/Vishal/Sreedevi/ Gokul/Divya |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated in 1p6 netlist |  |  |  | NA | NA | NA | NA | NA
4 | Move MLINK HDR closer to SoC by at least 15 cm in order to be within max length. | Will have impact to layout and TO timelines. | Aparna/Vishal/Sreedevi/ Abhijith |  |  | Yes | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Got a waiver; Change needed in ( SKU Name) RVP 03: Layout |  |  | Got waiver during ERB CST reviews |  | Same as RVP00 | Same as RVP01
5 | Short FPS connector pin 15 and 7 (INT) via ohm resistor to support old FPS card which has interrupt on pin 15. | Will have impact to layout and TO timelines. | Vishnu |  | yes | yes | Change needed in ( SKU Name) RVP 01: RVP01 & RVP05; Change needed in ( SKU Name) RVP 02: Yes; Change needed in ( SKU Name) RVP 03: No |  |  | Updated |  | NA | NA | NA | NA | Updated
6 | Need to change placement of tripads to have USB2_P4_WWAN_DN and USB2_P4_WWAN_DP gnd reference in L2 | GND Reference miss in L2 layer | Harshali/Naseef | eUSB2 |  |  | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Placement; Change needed in ( SKU Name) RVP 03: No |  |  | Pending
7 | USB OC GPIO connection to BOBCAT CEM slot (CEM slot pin - TBD) | Cannot intercept in ERB due to design freeze | Harshali/Naseef/Shubham | TCSS |  |  | All SKUs where we have dTBT (RVP1,RVP2, RVP6) | Yes | No | No | No | No | Yes | No |  |  | Pending |  |  |  | NA | NA | NA | Pending
8 | Need to move the USB2_P4 routinng away from James Town VR | Will have impact to layout and TO timelines. | Harshali | eUSB2 | No | Yes | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Yes; Change needed in ( SKU Name) RVP 03: Layout |  |  | Pending |  | NA | updated in ERB itself
9 | +V1P8S0IX is a dangling net with no generation point | It is a design bug identified after ERB TO | Aparna/Vishal/Sreedevi/ Gokul/Divya | PCH Strap | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
10 | RVP CSI BO in TOP layer needs to be changed as per the latest BO board. | Mutliple BOB and RSB change happened during TO. | Sreedevi/Vishnu | CSI | No | Yes | Yes | No | Layout | yes | yes | [5 empty] | Updated |  | Updated | Updated
11 | XTAL Routing imrovement feedback from SI team (Azniza) https://intel-my.sharepoint.com/:p:/p/mahesh_gunnam/ER_lNdcOSDBDvWF_Xqr0emABPQ2LXrVnsMYeTdf7mReAFQ?e=17g9rh | Feedback is shared late in WW19 | Mahesh G/ Priyan/Shubham | Layout | No | Yes | Yes | Yes | Layout | Yes | Yes | Yes | Yes |  |  |  | Updated in CRB TO |  | Updated | Updated | Yes | Yes | Pending | Pending
12 | Got confirmation from Wacom team that the Reset pin doesnt require 3.3v buffer. it can be directly connected. | Feedback received recently in WW20 | Vishal/Vishnu | Touch Pad | Yes | Yes | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated |  | Updated | Updated | Updated | Updated | Updated
13 | Please use 200k for Rc. Based on WCL updates, we have changed the value from 27k to 200k, and it has passed VCM. | Feedback received recently in WW21p4 | Harshali/Shubham | USB3 | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Updated |  |  |  | Yes | Yes | Yes | Yes
14 | Remove TP_DDI_AUX_DP & TP_DDI_AUX_DN; after checking N-1 EDS/with Owner | Feedback from RVP 04 CRR | Sreedevi/Vishnu | Display | Yes |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated in 1p6 netlist |  | Updated | Updated | Updated | Updated | Updated
15 | Remove GATE based LS for EDP BKT EN, Instead use the free pin in EDP level shifter | Feedback from RVP 04 CRR | Sreedevi/Vishnu | Display | Yes |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated |  | Updated | Updated | Updated | Updated | NA
16 | Sereies res on "DDI3_REF_PAD_CLK" is not needed Routing can be optimised | Feedback from RVP 04 CRR | Sreedevi/Vishnu | Display | Yes |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updatd |  | Updated | Updated | Updated | Updated | Updated
17 | R9D30 and R9E17 can be removed for optimisation | Feedback from RVP 04 CRR | Sreedevi/Vishnu | Display | Yes |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated |  | Updated | Updated | Updated | Updated | Updated
18 | TCP0 and TCP1 VD2 (TI) PD Controller Address change due to 108 TCSS layout port swap | TCSS 108 AIC | Harshali/ Naseef | TCSS | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | pending
19 | Addition of EMC caps for all M.2 TCSS modules | Feedback from RVP 04 CRR | Harshali/ Naseef | TCSS | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | updated
20 | Remove SUSCLK connection to WWAN connector; Remove all WWAN related circuits | Change to meet WWAN removal | Sreedevi/Abhijith | Connectivity | Yes | Yes | Change needed in ( SKU Name) RVP 01: RVP01; Change needed in ( SKU Name) RVP 02: No |  |  | Updated
21 | USB3 series jumper removal at VIN of USB3 LS | Feedback from RVP 04 CRR | Harshali/ Shubham | USB3 | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | updated |  |  |  | Yes | Yes | Yes | Yes
22 | Add pull up/ down resistor for MCIO PERESET gpio | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | updated |  |  |  | Yes | Yes | Yes | Yes
23 | GPP_C_3_PCH_SRCCLKREQB_0 is 3.3V GPIO. Connect to x4 CEM after LT 3.3V side. | Feedback from RVP 01 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | No | No | No | No | No | No |  |  |  | Updated |  |  |  | NA | NA | NA | NA
24 | X4/X8 SLOT HOT PLUG DETECT LT, move to S rail and make pullup resistor unstuffed | Feedback from RVP 01 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | No | No | Yes | Yes | Yes | Yes |  |  |  | Updated |  |  |  | Yes | Yes | Yes | Yes
25 | Change WWAN connector to x2 M.2 SSD and add Sideband signal components | change to meet PNP validation req after WWAN removal | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | No | No | Yes | Yes | No | No |  |  |  | Updated |  |  |  | Yes | Yes | NA | NA
26 | Connect PXPC DMI port to NIST SSD as Rework option | CCB request | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | No | No | No | No | No |  |  |  | Updated |  |  |  | NA | NA | NA | NA
27 | Change power for X4 clock request LT from A rail to S rail | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | No | No | No | No | No |  |  |  | Updated |  |  |  | NA | NA | NA | NA
28 | Add option to connect Power Enable of X4 slot directly to LS bypassing inverter circuit | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | No | No | No | No | Yes |  |  |  | Updated |  |  |  | NA | NA | NA | Pending
29 | Improve routing for SUSCLK from SOC to RTC pin of PCH | Feedback from RVP 04 CRR | Priyan/Shubham | Clock | No | Yes | RVP01 | Open | Layout | No | No | No | No |  |  |  | Updated |  | SUSCLK Routing change as RVP01 CRB | SUSCLK routing reviewed | NA | NA | NA | NA
30 | Remove SMBUS TP from SSD which don’t have I2C NIST. | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | Yes | yes | yes | Yes | Yes |  |  |  | Updated |  |  |  | yes | yes | Yes | Yes
31 | DMI_CLKREQB_PCH to DMI_CLKREQB_PCH_N | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Done | Yes | yes | yes | No | No |  |  |  | Updated |  |  |  | yes | yes | NA | NA
32 | connect GPP_B15_USB2_OC3_B_A_ISH_GP_6 to CPU_PCIE_BOBCAT_BSSB_TX for barlowridge OC | New request came after tapeout | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | No | No | No | No | Yes |  |  |  | Updated |  |  |  | NA | NA | NA | Pending
33 | R7B40 change to 0402 R6B15 change to 0402 | Feedback from RVP 02 CRR | Priyan/ Shubham | PCIe | Yes | Yes | RVP01 | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Updated |  |  |  | Yes | Yes | Yes | Yes
34 | I3C/ EC_I3C debug connection needs to be connected to TCP1 (default) and TCP0 with rework | Not applicable for ERB. RVP03 and RVP05 needs to be added | Harshali | TBT | Yes | Yes | Change needed in ( SKU Name) RVP 03: Yes |  |  | Updated
35 | Added enable to 3.3v for HDMI load switch. | Feedback from pharveen | Sreedevi/Vishnu | Display | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
35 | Change 200k resistor of RTC crystal feed back to 10M | Learning from ERB | Priyan/ Shubham | Clock | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated |  |  |  | Yes | Yes | Yes | Yes
36 | RTC circuitry optimised | Learning from ERB | Ramasai | power | Yes | yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
37 | N-1 to N Pwr sequence logic modified | Learning from ERB | Ramasai | power | Yes | yes | Change needed in ( SKU Name) RVP 01: rvp1,2,4; Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
38 | VDD2H internal LDO is isolated from 3p3a rail | Learning from ERB | Ramasai | power | Yes | yes | Change needed in ( SKU Name) RVP 01: rvp1,2,4; Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
39 | Diode removed from rsmrst signal and optimised it | Learning from ERB | Ramasai | power | Yes | yes | Change needed in ( SKU Name) RVP 01: rvp1,2,4; Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
40 | Need to swap eUSB2 P7 and P8 in all Skus | TTL requirement | Harshali | USB2 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
41 | Need to swap MC0CH1 clk for memory | Learning from ERB | Aparna/Vishal/Divya | Memory | Yes | Yes | Yes | No | No | No | No | No | No | No | NA | NA | Updated | Updated | NA | NA | NA | NA | NA | NA | NA
42 | +VCCPRIM_1P8 need to connect to DIPSW (SW8U2) and connect DIP SW output to ADC2 | Feedback from Rami | Guru | SINAI | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
43 | Stub on SPI0_CS0_R_N net: add an extra resistor in the trace to allow cut off this stub when not using TPM header | Feedback from Jeremy | Guru | SPI | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
44 | Remove voltage dividers from ADC_IN8 | Feedback from Rami | Guru | SINAI | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
45 | Add DISP UTILIY & Genlock signals to SMP Connector only in RVP03 | Feedback from Sreedevi | Guru | SMP | Yes | Yes | RVP03 | No | Need to review | No | No | [5 empty] | Updated
46 | EDM Implementation needs to be updated as per Jeremy Feedback | Feedback from Jeremy | Guru | SPI | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
47 | Connect CPU_ID2 and CPU_ID3 pins to EC IO Exp | Requirement for CPU Detection | Guru | EC | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
48 | CPU, HUB and GCD pins implementation as per review feedback | Feedback from Die owners | Guru | Debug | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
49 | Remove Bypass path from SOC SPI0 Isolation FET | Feedback from PRD owner | Guru | SPI | Yes | Yes | RVP02, RVP03, RVP04, RVP05, RVP06 | Yes | Yes | Yes | Yes | [5 empty] | Updated
50 | PCH_PCIE_EXTREFCLK_DP/DN (G5, G6) connect to SMP Connector | Requirement from Priyan | Guru | SMP | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Priyan to confirm
51 | Add PU on PCH_SYS_RESET_N in page 289 in RVP01, 02 & 04 to +VCCPRIM_3P3 rail | Requirement from PD team | Guru | PD | Yes | Yes | Yes | Yes | Need to review | Yes | Yes | Yes | Yes | Yes |  |  | Updated
52 | Change SNDW_RCOMP res to 0201 in page 404 | Feedback from Sreedevi | Guru | Audio | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
53 | PCHHOT Implementation as per feedback received | Feedback | Guru | PCH | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
54 | TTK3 G3 detection topology updated | Learning from ERB | Guru | Debug | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
55 | Add a pu to gate of mosfet with netname X4_PCIE_SLOT_PWR_EN_N based on GPIO pwr domain confirmation from pinmapping excel | Keeping this resistor backup option and will stuff/unstuff based on PO | Priyan/ Shubham | PCIE | Yes | yes | Yes | Yes | No | No | No | No | Yes |  |  |  | Updated |  |  |  | NA | NA | NA | Pending
56 | 0 ohm option will add in all sku as Dfx team asking for VNNAON increase to 100mV more | To increase VINON by 100mV | Ramasai | PD | Yes | Yes | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
57 | VCCIO VR power good masking | VCCIO VR powergood floating in current design | Ramasai | PD | Yes | Yes | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
58 | JBR changes for RVP02 and RVP03 as RBR is Zbbed | ERB its not applicable | Harshali |  | Yes | Yes | No | Yes | Yes | No | No | [5 empty] | NA
59 | GPP_CAM1_CLK_EN should have 0 OHM option from GPP_PRIVACY_LED_CAM1_CVS_HST_WAKE and keep it default empty | New requirement from ECG team | Sreedevi/Vishnu | Camera |  |  | Yes | No | No | No | No | [5 empty] | Pending
60 | Give 0 ohm bifurcation to PCIe slot power for giving toCamera connector | New requirement from ECG team | Sreedevi/Vishnu | Camera |  |  | Change needed in ( SKU Name) RVP 01: Yes |  |  | Updated in 1p6 netlist
62 | ADD side band signal from PCH for controlling X4 CEM slot as rework option with SOC GPIOs similar to Clock and clock request | INput from nex which was missed in ERB | Priyan | PCH GPIO | Yes | Yes | Yes | No | No | No | No | [5 empty] | Updated
63 | Replacing cap on VBUS with 0.1uF 100V for EMC requirement | Input from RVP04 | Harshali | TCSS modules | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated
64 | Virtual bateery circuit modification | Based on ERB PO learning | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated in 0p7 netllsit
65 | added 0 hom PCH PWR OK path for debug purpose. | Based on ERB PO learning | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated in 0p7 netllsit
66 | Added PD option for RMRST and PCH PWR OK PU supply | Based on ERB PO learning | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated in 0p7 netllsit
67 | Add series resistor on output of U6V1 IC which is WAKE from SoC going to CPU WAKE signal. Keep the resistor unstuffed as SOC dont use this wake. | Learning from WCL | Priyan/ Shubham | Storage | yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated in 0p7 netllsit |  |  |  | Yes | Yes | Yes | Yes
68 | Added PCH-IOE UART connection for Debug logs | New Requirement | Guru | Debug UART | Yes | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes |  |  | Updated in 1p7 netllsit
69 | Package length matching of mem CAC vs CLK miss - impacting mem routing & ATLC tuning | Packaging miss | Aparna/Vishal/Divya | Memory | No | Yes | Yes | Yes | No | Yes | Yes | Yes | Yes | Yes | NA | NA | Updated WW27P2 | Updated in ATLC | Updated in ATLC | Updated in ATLC | Updated in ATLC | Updated in ATLC | Updated in ATLC | Updated in ATLC | Updated in ATLC
70 | Duplicate - Deleted
71 | remove these R1D2,R1D14,R2D47 resistors | These are tripad resistors for WWAN. Since WWAN is removed these resistors are not needed | Harshali | USB3.2 |  |  | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: No; Change needed in ( SKU Name) RVP 03: Yes |  |  | Updated
72 | Need to add pullup resistor to Interrupt pin of SoC. SOC_INT_L | Interrupt will not have pullup | Vishnu | FPS | Yes | Yes | Change needed in ( SKU Name) RVP 01: Yes; Change needed in ( SKU Name) RVP 02: Yes; Change needed in ( SKU Name) RVP 03: Yes |  |  | Updated |  | Updated | Updated | Updated | Updated | Updated
73 | GSPI2_MISO need a 22E series resistor as per PDG | The current series resistor cant be placed near FPS since it is tripaded with SPI FLASH signals | Vishnu | FPS | yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Updated |  | Updated | Updated | Updated | Updated | Updated
74 | Need to have PUon SAR NIRQ INT pin | because WWAN is removed. we removed associated circuitry. So no PU rightnow for SAR NIRQ interrupt pin | Vishnu | ISH | yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Updated |  | NA | Updated | Updated | Updated | NA
75 | V1p8A pwr good PU voltage changed to V3p3A | ERB PO learnings | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
76 | R8A8 change to 10K | ERB PO learnings | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
77 | R3j41 make empty | ERB PO learnings | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
78 | 3x0805, 100uf caps addition on +VCCPRIM_VNNAON rail to meet transient responese | ERB PO learnings | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
79 | Provide Rework option from GPP PRIVACY LED gpio to GPP_CAM1_CLKEN pin | ECG requirement | Vishnu |  |  |  | Yes | No | No | No | No | [5 empty] | Updated |  | NA | NA | NA | NA | NA | NA
80 | I2S_TXD_CRD1 should be changed to I2S_RXD_CRD1. Also need to update in the SoC side - ECG team needs RXD signal instead TXD | ECG requirement | Vishnu |  |  |  | Yes | No | Yes | No | No | [5 empty] | Updated
81 | 2x 0805, 47uf caps addition on +VCCPRIM_IO rail to meet transient responese | ERB PO learnings | Ramasai |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
82 | REPLACE C2E3 & C2E5 with D70542-230 | XTAL shunt cap value mismatch with iPDG | Priyan/ Shubham | Xtal | yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Pending |  |  |  | Yes | Yes | Yes | Yes
83 | Remove SOC_M2_GEN4_X2_SSD5_PWREN from GPP_A_8_OSSE_SMLCLK_A_GSPI1_CLK |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
84 | Connect GPP_A_9_OSSE_SMLDATA_A_GSPI1_MOSI to SOC_M2_GEN4_X2_SSD5_PWREN |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
85 | Connect GPP_C_6_SML1CLK to WIFI_WAKE |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
86 | Connect GPP_C_7_SML1DATA to X1_SLOT_WAKE |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
87 | Remove X1_SLOT_WAKE from GPP_B_25_ESPI_ALERT1_B |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
88 | Remove WIFI_WAKE from GPP_A_13_ESPI_CS1_B |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
89 | Remove TP_M.2_WWAN_DISABLE_N ( R2T4) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
90 | Remove TP_M.2_WAKE_ON_WWAN_N (R2E100) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
91 | Remove NC_SAR_DPR_PCH R1F3 |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
92 | Remove TP_M.2_GNSS_DISABLE_N (R9B41) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
93 | Remove TP_M.2_WWAN_RST_N (R1E39), NC_CNV_MFUART2_TXD (R1E43), NC_CNV_MFUART2_RXD (R1E45) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
94 | Remove TP_M.2_WWAN_TIME_SYNC_1 (R1R21) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
95 | PCH GPP_J14 and GPP_J17 swapped for X4 Slot PWREN |  | Gokul/Divya |  | Yes | Yes | Yes | Yes | No | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
96 | Remove NC_WWAN_WAKE_GPIO_N ( R2F15 N) |  | Gokul/Divya |  | Yes | Yes | Yes | No | Yes | No | No | No | No | No |  |  | Updated |  |  |  | NA | NA | NA | NA | NA
97 | Tant cap removed for usb3 and replaced with 4 ceramic caps | PPV Team requirmem=nt | Harshali/ Shubham |  |  |  | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Updated |  |  |  | Yes | Yes | Yes | Yes
98 | Add a 10K PU to 198A rail on RESET_SYNC_N signal | Giving an option for RVP. It may not be needed |  |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
99 | Add a 10K PD on BIOS_READY signal | BIOS ready usage is nor clear. So giving an option not to make this signal float |  |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
100 | Follow this strap setting as per RVP-04 " GPP_R2_HDA_SDO_I2S0_TXD_A_HDACPU_SDO" | Doing optimization in RVP |  |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
101 | Remove this net " TP_RECVRY_INDICATOR_FDO_PCH" | TP optimization |  |  |  |  | Yes | Yes | Yes | Yes | Yes | [5 empty] | Updated
102 | Stuff R2F44 - By deafult stuffing x2 SSD RST path and MCIO path as rework | [5 empty] | Yes | No | No | Yes | Yes | [5 empty] | Updated
103 | CR6m1 unstuff | Learning from WCL. The reverse leakage on EC prochot line has caused this loading and CPU throttling | Priyan |  |  |  | Change needed in ( SKU Name) RVP 02: Yes |  |  | Updated
104 | PCH: eSPI needs be disabled in straps, if eSPI port is not used Refer notes for each GPIO straps for PU/PD stuffing--> ignore this comment GPD_12 Should be high. Since it is RSMRST and DSW_PWROK tied together, it will be sampled at RSMRST. GPD_7 should be low PCD: GPP_D3 Should be enabled high for PCH IOE | straps review comments | Gokul/Divya | Straps | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | [6 empty] | Updated | Updated
105 | Added Filter cap near soc for SUSCLK clock connection to RTC pin of PCH |  | Priyan/ Shubham |  |  |  | Yes | NO | NO | No | No | No | No | No | [6 empty] | NA | NA | NA | NA
106 | Make PCD UART default debug path & PCH path as rework |  | Guru/Divya/Gokul | debug UART | Yes | No | Yes | Yes | Yes | Yes | Yes | No | No | No | [6 empty] | Updated | Updated | NA | NA | NA
107 | Stuff Pull-Down Res on JTAGX ODT Disable Strap (GPP_E6) with 4.7K Stuff Pull-Down Res on JTAGX ODT SELECTION (VAL_MIPI60_PCD_JTAGX) with 1K Also please change VCC for strap JTAGX ODT SELECTION to +VCCIO_TERM_V1P25, since there is no +VCCPRIM_1P25 in RVP05 | Learning from NVL-S | Guru/Divya/Gokul | JTAG straps | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated |  | Updated | Updated | Updated | Updated | Updated
108 | Add I3c connection to NIST SSD from MECC ADD IN CARD | No I3C support on onboard EC, MECC support only on RVP03 | Priyan/ Shubham |  |  |  |  | No | Yes | No | No | Yes | No | [7 empty] | NA | NA | Yes | NA
109 | Changing PU to 10K on VNNAON PWRGD | Validation finding(pwrgd vtg not reflecting to full value) | Ramasai |  |  |  | yes | yes | Yes | yes | yes
110 | Make X1/ X4/ X8 SLOT Bulk caps EMPTY (In HSIO pages only) | Optimization proposed by PD team | Priyan/ Shubham |  | Yes | No | Pending | Pending | Pending | Yes | Yes | Yes | Yes | [7 empty] | Pending | Pending | Yes | Yes
111 | Make PSS Ext ANT section removed/ EMPTY | Part of Optimization | Guru/ Shubham |  | Yes | Yes | Change needed in ( SKU Name) RVP 04: yes; Change needed in ( SKU Name) RVP 04-m: yes; Change needed in ( SKU Name) RVP 05: Yes; Change needed in ( SKU Name) RVP 06: Yes | [6 empty] | Pending | Pending | Yes | Yes
112 | Provide ground void depth of more than 230um for WLAN step signals at M.2 connector |  | Abhijith |  | No | Yes | yes | yes | yes | yes | yes | yes | yes
113 | Camera PMIC adress update | Camera PMIC adress update | Vishnu |  |  |  | Yes | Yes | Yes | Yes | Yes
114 | Stuff PCD JTAG On board termination resistors TMS, TDI, PREQ stuff PU with 51 Ohms PRDY, TDO, JTAG_MBPB [0:1] stuff PU with 100 Ohms TCK stuff PD with 51 Ohms Stuff Pull-Down Res on JTAGX ODT Disable Strap (GPP_E6) with 4.7K Stuff Pull-Down Res on JTAGX ODT SELECTION (VAL_MIPI60_PCD_JTAGX) with 1K | Learning from NVL-S | Guru | JTAG ODT | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Updated |  | Updated | Updated | Updated | Updated | Updated
115 | Unstuff HUB_VIEWANA PD resistors | Learning from NVL-S | Guru | Debug | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Pending |  | Updated | Updated | Updated | Updated | Updated
116 | Unstuff VREF_ADC LDO | ERB PO learnings | Ramasai/Guru | Power | Yes | No | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |  |  | Pending |  | Updated | Updated | Updated | Updated | Updated
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200

## ERB PO Learning
SL No | Learnings /issue Description | Change needed in ( SKU Name) | Reason for not implemented in ERB ( if applicable) | Applicable for WW37 Pre-PO Board? | DE owner | Implementation status | RVP Sch rev | HSD link | Remarks
1 | Need to swap MC0CH1 clk for memory | RVP-1 | - wrong implementation from mRSB file - missed in ERB review cycles | Yes | Aparna | Updated